## Milestones
Task | Lead | Planned | Forecast | Progress | RAG
Discovery & data audit | L. Bianchi | 2026-02-15 | 2026-02-20 | 100 | Green
Elasticity model rebuild | G. Petrova | 2026-04-30 | 2026-05-08 | 85 | Amber
Pilot on 2 categories | L. Bianchi | 2026-06-30 |  | 40 | Amber
Full price-book rollout | J. Okafor | 2026-09-30 |  | 0 | Planned

## Value
Value driver | Category | Target | Realised | Quarter
Margin uplift from repricing | EBITDA | 1,600,000 | 350,000 | Q2 2026
Discount leakage reduction | Cost savings | 600,000 | 180,000 | Q2 2026